CAPSTONE PROJECT REPORT

AI-POWERED EXAMINATION AND PROGRAMMING PRACTICE PLATFORM FOR FPT UNIVERSITY

(APE)

Report 2 – Project Management Plan

Group: SEP490-G26

Lecturer: Nguyễn Mạnh Hiển

– Hanoi, June 2026 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	6

1.3 Project Risks	7

2. Management Approach	8

2.1 Project Process	8

2.2 Quality Management	9

2.3 Training Plan	9

3. Project Deliverables	10

4. Responsibility Assignments	11

5. Project Communications	13

6. Configuration Management	13

6.1 Document Management	13

6.2 Source Code Management	13

6.3 Tools & Infrastructures	13

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 06/06/2026 | A | Nguyễn Việt Đức | 1. Overview 2. Management Approach |
| 07/06/2026 | A | Nguyễn Việt Đức | 3. Project Deliverables 4. Responsibility Assignments |
| 09/06/2026 | A | Nguyễn Việt Đức | 5. Project Communications 6. Configuration Management |
| 11/06/2026 | M | Nguyễn Việt Đức | 1.2 Project Objectives 2.1 Project Process 2.2 Quality Management |
| 19/06/2026 | M | Nguyễn Việt Đức |  |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

Scope: The project is delivered within the 15-week Capstone Project timeline at FPT University, covering documentation, implementation, and testing.

Estimation: Each Work Breakdown Structure (WBS) item is assigned a complexity level (Simple, Medium, Complex) and an estimated effort in man-days; group rows are subtotals of their items. Complexity convention - Simple: 2–4 md; Medium: 5–7 md; Complex: 8–12 md. Estimates are allocated across 5 members (4 Developers + 1 Business Analyst) and include design, implementation, unit testing, system testing and integration testing per item.

| WBS | Item | Complexity | Est. (man-days) |
| --- | --- | --- | --- |
| 0 | Foundation & Infrastructure |  | 20 |
| 0.1 | Infrastructure Setup (CI/CD GitHub Actions, MongoDB, Judge0 self-host) | Complex | 8 |
| 0.2 | FE foundation (design system, routing, API client, auth guard, notification bell + SignalR client) | Medium | 6 |
| 0.3 | BE foundation (Clean Architecture skeleton, Mongo repository layer, global error handling, logging) | Medium | 6 |
| 1 | MF-01 — AI-Powered Document Ingestion & Vectorization (SRS §3.5) |  | 66 |
| 1.1 | System Documents (SA list) | Simple | 4 |
| 1.2 | Document Detail + Debug / Extraction Draft tab (SA) | Medium | 5 |
| 1.3 | Personal Documents (Student list) | Simple | 3 |
| 1.4 | Upload (BYOS) UI + validation (6 formats, 20 MB) | Medium | 5 |
| 1.5 | Preview + AI Gatekeeper (classify vs. course) | Complex | 9 |
| 1.6 | Duplicate Check (2-tier checksum, reuse) | Medium | 5 |
| 1.7 | Extract + Normalize + Vision Reinjection | Complex | 9 |
| 1.8 | Chapter Detection + Chunking | Complex | 7 |
| 1.9 | Vector Embedding & Storage | Medium | 6 |
| 1.10 | Auto-Tag (from seeded TopicTags) | Medium | 5 |
| 1.11 | Ingest background-job infra (SignalR progress, reconnect, persistence) | Complex | 8 |
| 2 | MF-02 — Chapter-Aware AI Question Generation (SRS §3.6) |  | 37 |
| 2.1 | Generation Config UI | Medium | 5 |
| 2.2 | MCQ Generation (+ explanation, difficulty formula) | Complex | 9 |
| 2.3 | PE / Coding Generation (+ test cases incl. hidden) | Complex | 9 |
| 2.4 | Question fingerprint dedup (semantic + scope isolation) | Medium | 6 |
| 2.5 | Review pipeline (Rule-based + LLM Cross-Review) | Complex | 8 |
| 3 | MF-03 — Isolated Coding Workspace & Judge0 Auto-Grading (SRS §3.10) |  | 22 |
| 3.1 | Coding Session (Monaco, run/submit, draft save, timer) | Complex | 9 |
| 3.2 | Judge0 integration (self-hosted, time/mem limits, 100% pass) | Complex | 9 |
| 3.3 | Submission Result | Simple | 4 |
| 4 | MF-04 — On-Demand AI Code Mentor (SRS §3.11) |  | 8 |
| 4.1 | AI Code Mentor (static analysis, structured feedback, cap 3/attempt) | Complex | 8 |
| 5 | MF-05 — Practice & Flashcards (SRS §3.8–§3.9) |  | 23 |
| 5.1 | Practice Setup (2 sources, cascading select, difficulty + count / cap logic) | Complex | 8 |
| 5.2 | MCQ Session (count-up timer, Retry All / Wrong, resume) | Medium | 6 |
| 5.3 | MCQ Result (list + correct answer + explanation) | Simple | 4 |
| 5.4 | Flashcard Session (flip, difficulty filter) | Medium | 5 |
| 6 | MF-06 — Knowledge Analytics (SRS §3.12) |  | 21 |
| 6.1 | Progress Dashboard (Student) | Medium | 6 |
| 6.2 | Practice History | Simple | 4 |
| 6.3 | Admin Dashboard | Medium | 5 |
| 6.4 | Analytics — All Students (+ Absorbed Loss) | Medium | 6 |
| 7 | MF-07 — VND Wallet & Pay-Per-Use Monetization (SRS §3.2) |  | 25 |
| 7.1 | AI Wallet (balance + ≥ 1000 VND guard) | Medium | 5 |
| 7.2 | Top-up + PayOS (checkout, webhook, reconcile) | Complex | 9 |
| 7.3 | Top-up History | Simple | 3 |
| 7.4 | Billing engine (charge points, Absorbed Loss, Usage Log) | Complex | 8 |
| 8 | MF-08 — Advanced AI Configurator (SRS §3.13) |  | 39 |
| 8.1 | AI Configuration Hub | Simple | 3 |
| 8.2 | Provider Credentials | Medium | 5 |
| 8.3 | AI Agents (6 agents ↔ Preset switch) | Medium | 6 |
| 8.4 | Prompts (Monaco editor, versioned) | Medium | 6 |
| 8.5 | Rule Artifacts (Monaco, JSON) | Medium | 6 |
| 8.6 | AI Smoke Test | Medium | 5 |
| 8.7 | AI Usage Logs | Simple | 4 |
| 8.8 | AI Billing & Absorbed Loss (view) | Simple | 4 |
| 9 | MF-09 — Course & Question Bank Management (SRS §3.3, §3.4, §3.7) |  | 34 |
| 9.1 | Course CRUD + Activate / Deactivate | Medium | 6 |
| 9.2 | Topic Tag CRUD + Import | Medium | 5 |
| 9.3 | Question Bank Browse (Student, topic filter) | Medium | 5 |
| 9.4 | Question Detail | Simple | 3 |
| 9.5 | Review Draft Questions (Personal) + Publish-all | Medium | 5 |
| 9.6 | Moderate Draft Questions (System) — SA Publish / Reject | Medium | 5 |
| 9.7 | System Question Bank (SA disable / delete) | Medium | 5 |
| 10 | MF-10 — Authentication & Profile (SRS §3.1) |  | 16 |
| 10.1 | Login (Google OAuth 2.0) | Medium | 5 |
| 10.2 | Student Home | Simple | 3 |
| 10.3 | Profile (view / edit) | Simple | 3 |
| 10.4 | JWT + Role-based Authorization (2 roles) | Medium | 5 |
| Total Estimated Effort (man-days) |  |  | 311 |

### 1.2 Project Objectives

Overall Objective: Successfully build and deliver APE — an AI-integrated coding-practice and exam-preparation platform for FPT University students — within the 15-week Capstone timeline (including a 9-week implementation phase), ensuring product quality, on-time delivery, and adherence to the team’s resource constraints.

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Code Review (PR) | 100% PRs | 50 | 33.33% | Mandatory reviewer approval before merging to develop; catches logic, naming, SOLID, and design issues early. |
| 2 | Unit Test | ≥ 70% business logic | 45 | 30.00% | Jest (ReactJS FE) + xUnit (.NET BE); developers cover all complex business-logic functions. |
| 3 | Integration Test | 100% API endpoints | 30 | 20.00% | Postman / Swagger at the end of each Sprint; validates API contracts and inter-module communication. |
| 4 | System Test | All features (MF-01–MF-10) | 18 | 12.00% | Conducted in Sprint 9; functional, performance, and security testing over the full feature tree + PayOS. |
| 5 | Acceptance Test | 8 core workflows | 7 | 4.67% | Live demo with the Lecturer; end-to-end business workflows; 0 Critical defects allowed. |
|  | Total (defect budget) |  | 150 | 100% |  |

Milestone Timeliness (%):

- Milestone Timeliness: ≥ 90% of deliverables submitted on or before the deadline.

- Sprint Completion Rate: ≥ 85% of committed story points completed each Sprint.

- Acceptance Quality: 0 Critical / Blocker defects at the final Acceptance demo.

Allocated Effort (man-days):

- Total Estimated Effort: 311 man-days across 5 members (inclusive of all activities per WBS item — design, implementation, unit and integration testing).

- Business Analyst (1): leads requirements, design, and documentation; contributes across all phases.

- Development & Testing (4 Developers): execute all WBS items including coding, unit testing, and integration testing per Sprint.

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Third-party API downtime (OpenAI/Google LLM, Judge0): High system dependency on external services | High | Medium | Implement circuit breakers + fallback messages; apply Model Routing—automatically switch to a backup provider when the primary provider goes down (OpenAI <-> Google); cache recent AI results to serve temporarily. |
| 2 | AI Hallucination: Generator produces incorrect questions/code, and Critic fails to detect them | High | Medium | Apply a 3-layer pipeline: (1) RAG Strictness - force the AI to only use knowledge within the Vector DB. (2) Actor-Critic - Agent 2 reviews Agent 1, retry maximum 2 times. (3) Structured JSON Output - parse and validate the schema before saving. Mandate Admin censorship before publishing. |
| 3 | Team members lack experience with the new tech stack (.NET, Judge0 API, Vector DB, LangChain) | Medium | High | Conduct centralized training in Week 1 by domain; implement pair programming between senior and junior members within the team; host knowledge-sharing sessions at the end of each Sprint; document technical decisions in ADR (Architecture Decision Record). |
| 4 | Scope creep: BYOS and Payment features are more complex than expected; AI pipeline receives new requirements from Lecturer | High | Medium | Apply MoSCoW method: Payment = Nice-to-have; BYOS BYOK = Should-have; prioritize FE01–FE05 as Must-have. Freeze scope after Sprint 3; add all new requirements to the backlog, do not introduce them into the current Sprint. |
| 5 | Token cost exceeds budget: ~5,000–8,000 tokens/session (~50–100 VND/exercise). Continuous testing can cost millions of VND | Medium | High | Mandate BYOK in dev/test environments; apply Model Routing—use Gemini 2.5 Flash / GPT-4o-mini for Gatekeeper, Tagging, and FE Generator; only use Gemini 2.5 Pro / GPT-4o for Code Mentor and PE Generator; set a hard limit on tokens/day via API Cost Tracker (FE-07). |
| 6 | Judge0 returns inconsistent results under high load or timeout issues, affecting PE grading | Medium | Medium | Restrict supported languages to (C, C++, Java, Python); set a hard timeout for each submission; write integration tests covering each language; clearly display TLE/RTE statuses instead of generic system errors. |
| 7 | PE Generator Retry Loop out of control: Critic fails continuously or Judge0 reports consecutive connection errors, causing infinite backend AI calls, API cost spikes, and hung requests | Hight | Medium | Enforce a hard limit of maximum 2 retries at the backend layer (independent of AI self-decision); return a clear error message to the user after 2 failures; log all retry attempts into monitoring; set a 30s request timeout for each AI call. |
| 8 | Incorrect Overwrite Submission logic: The final submission overwrite mechanism (Resubmit → Overwrite) if implemented incorrectly can cause a race condition when multiple users submit simultaneously, leading to learning data loss | Medium | Medium | Apply Optimistic Locking or transaction-level write on MongoDB; disable the Submit button immediately after the first click (debounce on FE); write unit tests for the submission overwrite logic; log a separate submission history for auditing if needed. |

## 2. Management Approach

### 2.1 Project Process

The team adopts the Agile Scrum framework with 1-week Sprints across the 9-week implementation phase (Phase 2), with a team of 5 members. Documentation and analysis (Reports 1–3) are produced during Phase 1; Phase 2 delivers the product through nine Sprint releases. Each Sprint follows the cycle: Sprint Planning → Daily Standup → Development & Testing → Sprint Review → Retrospective.

Sprint allocation (Phase 2 — mapped to the MF-01–MF-10 feature tree):

| Sprint (Week) | Feature Focus |
| --- | --- |
| Sprint 1 (W1) | Foundation & Infrastructure (CI/CD, Docker, MongoDB, self-hosted Judge0) · MF-10 Authentication & Profile |
| Sprint 2 (W2) | MF-07 VND Wallet & PayOS · MF-09 Course & Topic Tag management |
| Sprint 3 (W3) | MF-01 Ingestion (part 1): Upload / BYOS, AI Gatekeeper, Duplicate check, Extract & Normalize |
| Sprint 4 (W4) | MF-01 Ingestion (part 2): Vision reinjection, Chapter / Chunk, Vector embedding, Auto-Tag, background jobs · MF-08 Configurator core (providers, agents, prompts, rule artifacts) |
| Sprint 5 (W5) | MF-02 Chapter-Aware Question Generation (MCQ + PE) with fingerprint dedup & review pipeline |
| Sprint 6 (W6) | MF-03 Coding Workspace + Judge0 grading · MF-04 AI Code Mentor |
| Sprint 7 (W7) | MF-05 Practice & Flashcards · MF-09 Question Bank (browse, review, moderation) |
| Sprint 8 (W8) | MF-06 Knowledge Analytics (Student + Admin) · MF-08 Configurator observability (smoke test, usage logs, billing & absorbed-loss) |
| Sprint 9 (W9) | System & Acceptance testing, regression, bug fixing, demo preparation |

### 2.2 Quality Management

The team applies a multi-layered testing strategy to ensure product quality throughout the development lifecycle:

| Approach Name | Detail | Quality Objectives |
| --- | --- | --- |
| Code Review (Pull Request) | Every Pull Request requires at least one reviewer approval before merging into develop. The reviewer checks code logic, naming conventions, SOLID / Clean Code compliance, security, and test coverage. | Catch design and logic defects early; ensure code quality and consistency across the team; reduce downstream defects. |
| Unit Test | Applied to complex business-logic functions. Stack: Jest (ReactJS Frontend), xUnit (.NET Backend). Tests are written alongside feature code; target coverage ≥ 70%. | Validate that individual functions work correctly in isolation; ensure regression safety when code changes. |
| Integration Test | All API endpoints are tested with Postman / Swagger at the end of each Sprint, covering request/response contracts, authentication flows, and data integrity between Frontend and Backend. | Verify that internal modules and external services (Judge0, LLM Cloud Service, PayOS) communicate correctly; detect interface mismatches early. |
| System Test | Conducted in Sprint 9 over all features (MF-01–MF-10). Includes functional, performance, and security testing across the full feature tree. | Ensure the system meets the architecture design and functional requirements; validate end-to-end feature completeness. |
| Acceptance Test | Live demo with the Lecturer during the final Review session, focused on 8 core business workflows: (1) Google Login, (2) Wallet Top-up via PayOS, (3) System Document Ingestion, (4) BYOS Ingestion, (5) AI Question Generation & Review, (6) MCQ / Flashcard Practice, (7) Coding Practice via Judge0, (8) AI Code Mentor. | Confirm the system satisfies user expectations and business objectives; achieve 0 Critical defects; demonstrate readiness for deployment. |

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| .NET Web API & Clean Architecture | Vũ Hoàng Anh | Week 1, 3 days | Mandatory |
| ReactJS + TypeScript | Phan Duy Hưng | Week 1, 2 days | Mandatory |
| MongoDB Schema Design | Nguyễn Viết Sang, Phạm Quốc Minh | Week 1, 1 day | Mandatory |
| OpenAI / Gemini API & Prompt Engineering | Phạm Quốc Minh | Weeks 1–2, self-study | Mandatory |
| Judge0 API Integration | Phạm Quốc Minh | Week 2, 1 day | Mandatory |
| Docker & CI/CD (GitHub Actions) | All members | Week 1, 1 day | Optional |
| Git Flow & Code Review Process | All members | Day 1 of Sprint 1 | Mandatory |
| Business Analysis & SRS Writing | Nguyễn Việt Đức | Week 1, self-study | Mandatory |

## 3. Project Deliverables

| # | Deliverable | Due Date | Responsible | Notes |
| --- | --- | --- | --- | --- |
| PHASE 1 – FIRST 5 WEEKS: Documentation & Analysis (Report 1, 2, 3) |  |  |  |  |
| 1 | Report 1 – Project Introduction | Week 3 | Việt Đức (BA) | … |
| 2 | Report 2 – Project Management Plan | Week 4 | Việt Đức (BA) |  |
| 3 | Report 3 – Software Requirements Specification (SRS) | Week 4-5 | Việt Đức (BA) | Use Cases, Functional & Non-functional Req, API Specs |
| PHASE 2 – 9 WEEKS OF CODING: Development & Documentation (Report 4, 5, 6, 7 + Sprint Releases) |  |  |  |  |
| 4 | Report 4 – Software Design Document (SDD) | Coding Weeks 2–3 | Việt Đức (BA) + Dev Lead | System Architecture, DB Schema, API Design, Sequence Diagrams |
| 5 | Sprint Release 1–3 – Auth, Data Ingestion, AI Gatekeeper | Coding Weeks 1–3 | 4 Devs | FE-09, FE-01 complete; deployed to Dev env |
| 6 | Sprint Release 4–6 – FE/PE Generator, Judge0, Exam Workspace | Coding Weeks 4–6 | 4 Devs | FE-02, FE-03 complete; core AI features live |
| 7 | Sprint Release 7–8 – Analytics, Gamification, Dashboard, AI Configurator | Coding Weeks 7–8 | 4 Devs | FE-04, FE-05, FE-06, FE-07 complete |
| 8 | Sprint Release 9 – Payment, System Testing, Bug Fix | Coding Week 9 | 4 Devs | Feature complete; FE-08, Payment; regression test pass |
| 9 | Report 5 – Test Documentation & Test Report | Coding Weeks 8–9 | 4 Devs | Test Plan, Test Cases, Defect Log, Unit/Integration/System Test Report (.docx + .xlsx) |
| 10 | Report 6 – Software User Guides | Coding Week 9 | 4 Devs | User manuals for Admin, Student, and Super Admin |
| 11 | Report 7 – Final Project Report | Coding Week 9 | 4 Devs | Project summary: objectives, achievements, and lessons learned |
| 12 | Final Demo & Capstone Presentation | Presentation Week | Whole Team | Live system demo + slide deck for the Capstone Review Committee |

## 4. Responsibility Assignments

D ~ Do; R ~ Review; S ~ Support; I ~ Informed; <blank> - Omitted

| Responsibility | Vũ Hoàng Anh (Leader/Dev/BA) | Nguyễn Việt Đức (BA/Docs) | Phan Duy Hưng (Dev) | Phạm Quốc Minh (Dev/Test) | Nguyễn Viết Sang (Dev/BA) |
| --- | --- | --- | --- | --- | --- |
| PHASE 1 – FIRST 5 WEEKS: Documentation & Analysis |  |  |  |  |  |
| Project Planning & Tracking (Whole Project) | R | D | I | I | I |
| Report 1 – Project Introduction | R | D | S | S | S |
| Report 2 – Project Management Plan | R | D | S | I | I |
| Report 3 – SRS (Use Cases, Req, API Specs) | R | D | S | S | S |
| PHASE 2 – 9 WEEKS OF CODING: Development, Testing & Documentation |  |  |  |  |  |
| Report 4 – Software Design Document | R | D | S | S | S |
| Infrastructure Setup (CI/CD, Docker, MongoDB) | D | I | R | S | S |
| FE-09: Authentication Module | D | R | S | S | S |
| FE-01: Data Ingestion & AI Gatekeeper | R | I | D | S | S |
| FE-02: FE Generator (MCQ) | S | R | S | D | S |
| FE-02: PE Generator + Judge0 Validation Loop | S | R | D | S | S |
| FE-03: Exam Workspace & Judge0 Integration | R | I | D | S | S |
| FE-03: AI Code Review | S | R | S | S | D |
| FE-04: Knowledge Analytics & AI Study Advice | S | R | S | S | D |
| FE-05: Gamification System | I | R | S | D | S |
| FE-06: AI Configurator | D | R | S | S | S |
| FE-07: System Dashboard & User Management | D | I | S | R | S |
| FE-08: Course & Question Bank Management | R | I | S | S | D |
| Payment Management | R | I | D | S | S |
| Report 5 – Test Documentation & Test Report | S | D | R | R | R |
| Unit Testing (BE) | S | R | D | D | S |
| Unit Testing (FE) | S | R | R | S | D |
| Integration & System Testing | R | D | S | S | S |
| Report 6 – Software User Guides | R | Đ | I | I | I |
| Report 7 – Final Project Report | R | D | S | S | S |
| Final Demo Preparation | D | R | R | R | R |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Daily Standup | All 5 members | Sync progress, identify daily blockers | Daily, 1 hour (9:30 PM) | Online - Discord |
| Sprint Planning | All 5 members | Plan tasks for the new Sprint | Start of each Sprint (Monday) | Offline meeting - GitHub Projects |
| Sprint Review & Demo | Team + Lecturer | Demo Sprint results, gather feedback | End of each Sprint (Next Wed) | Offline Meeting |
| Sprint Retrospective | All 5 members | Improve working processes | End of each Sprint, 30 minutes | Online – Discord |
| Weekly Report to Lecturer | Whole team -> Lecturer | Report progress & impediments | Weekly (Wed) | Email / Offline Meeting |
| Code Review | Developer | Ensure code quality before merging | Every Pull Request | GitHub PR Comments |
| Issue Tracking | All 5 members | Track bugs, tasks, and features | Continuous | GitHub Issues |
| Document Sharing | All 5 members | Share & collaborate on documents | Continuous | Google Drive |

## 6. Configuration Management

### 6.1 Document Management

All project documents are stored centrally on Google Drive with a folder structure organized by Sprint and document type (Reports, Meeting Minutes, Design Docs). Naming convention:

[ProjectCode]_[DocType]_[Version]_[Date].docx (e.g., APE_Report2_v1.0_09062026.docx).

Each document must include a Record of Changes on the first page. Only the Leader and designated assignees have edit permissions; other members are restricted to comment-only mode.

### 6.2 Source Code Management

Source code is managed on GitHub utilizing the GitFlow branching strategy: main (production), develop (integration), feature/[feature-name] (individual features), and hotfix/[issue] (urgent bug fixes). Pull Requests strictly require at least 1 reviewer approval before merging into develop. Commit messages must follow the Conventional Commits standard (feat:, fix:, docs:, test:, chore:). GitHub Actions will automatically trigger build + unit tests upon PR creation.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology (Frontend) | ReactJS + TypeScript, TailwindCSS, Axios, React Query |
| Technology (Backend) | .NET 8 Web API |
| AI / LLM – Tier 1 (Fast & Cheap) | Gemini 2.5 Flash mini, GPT-4o-mini → Used for: AI Gatekeeper, Auto-Tagging, FE Generator (MCQ). Advantages: < 1s latency, cost in millicents/request |
| AI / LLM – Tier 2 (Deep Reasoning) | Gemini 2.5 Pro, GPT-4o \(\rightarrow \) Used for: AI Code review (AST/Semantic analysis), PE Generator (algorithm + test inputs). Ensures pedagogical quality |
| Database | MongoDB Atlas (Primary) |
| Code Execution Engine | Judge0 API (Docker-based, supports C, C++, Java, Python) |
| IDEs / Editors | Visual Studio 2022 (BE), Visual Studio Code (FE) |
| Diagramming | DrawIO, PlantUML, Figma (UI Mockup) |
| Documentation | Google Docs/Sheets, Microsoft Office |
| Version Control | GitHub |
| Deployment / Cloud | MongoDB Atlas |
| Project Management | GitHub Projects |
| Communication | Discord (Daily), Google Meet (Meetings), Gmail (Formal) |