## WBS
PROJECT WORK BREAKDOWN STRUCTURE
# | Function/Screen | Layer | Feature | Level* | Function/Screen Details | Planned | Status
1 | Login Screen Layout | FE | Common | Simple | Render login page layout and login card UI | Week 5 | Done
2 | Google Sign-in Action | FE | Common | Medium | Handle Google identity token login request from login page | Week 5 | Done
3 | Auth Session Storage | FE | Common | Medium | Persist access token, refresh token, and user session in storage | Week 5 | Done
4 | Session Refresh Flow | FE | Common | Medium | Refresh expired session and reload authenticated user profile | Week 5 | Done
5 | Protected Route Guard | FE | Common | Medium | Protect student and admin routes for unauthenticated access | Week 5 | Done
6 | Role-based Home Redirect | FE | Common | Medium | Redirect authenticated user to dashboard based on role | Week 5 | Done
7 | Theme Persistence | FE | Common | Simple | Store and restore selected UI theme | Week 5 | Done
8 | Topbar Logout Action | FE | Common | Simple | Logout current user and clear session state | Week 5 | Done
9 | Profile Information View | FE | Common | Simple | Display current user profile information on profile page | Week 5 | Done
10 | Dashboard Summary Widgets | FE | Student | Medium | Render student dashboard summary cards and overview content | Week 5 | Done
11 | Dashboard Navigation Shortcuts | FE | Student | Simple | Provide quick links from dashboard to key student workflows | Week 5 | Done
12 | Student Journey Timeline | FE | Student | Medium | Render learning journey timeline and milestone view | Week 6 | Done
13 | Student Journey Progress Signals | FE | Student | Simple | Display progress indicators in learning journey page | Week 6 | Done
14 | Exam Config Course Selection | FE | Student | Medium | Select course before starting exam configuration | Week 6 | Done
15 | Exam Config Question Pool View | FE | Student | Medium | Show question pool information for selected exam settings | Week 6 | Done
16 | Exam Start Request | FE | Student | Medium | Submit request to start configured exam session | Week 6 | Done
17 | PE Exam Config View | FE | Student | Medium | Render programming exam configuration screen | Week 6 | Done
18 | PE Exam Start Flow | FE | Student | Medium | Trigger PE exam start flow from configuration page | Week 6 | Done
19 | FE Live Exam Question View | FE | Student | Complex | Render MCQ exam questions and answer options | Week 6 | Done
20 | FE Live Exam Answer Selection | FE | Student | Complex | Track selected answers during FE live exam | Week 6 | Done
21 | FE Live Exam Submission | FE | Student | Complex | Submit FE exam answers and receive scoring result | Week 6 | Done
22 | Coding Practice Launch View | FE | Student | Medium | Open coding practice launch page and mode selection | Week 6 | Done
23 | Coding Practice Resume Session | FE | Student | Medium | Resume active coding practice session from launch flow | Week 6 | Done
24 | Practice Library Listing | FE | Student | Medium | List available practice exams and practice entries | Week 6 | Done
25 | Practice Library Filtering | FE | Student | Simple | Filter practice library items by available options | Week 6 | Done
26 | System Exam Library Listing | FE | Student | Medium | List generated or system-managed exam library entries | Week 6 | Done
27 | Exam Library Pagination | FE | Student | Simple | Navigate pages of student exam library results | Week 6 | Done
28 | Practice History Listing | FE | Student | Medium | Display practice and exam attempt history | Week 7 | Done
29 | Practice History Detail Navigation | FE | Student | Simple | Open past result details from practice history | Week 7 | Done
30 | Result Viewer Summary | FE | Student | Medium | Show score summary and overall evaluation for a submission | Week 7 | Done
31 | Result Viewer Detailed Feedback | FE | Student | Complex | Render detailed answer result or grading feedback view | Week 7 | Done
32 | Question Bank Listing | FE | Student | Medium | Show student-accessible question bank list | Week 7 | Done
33 | Question Bank Search & Filter | FE | Student | Medium | Search and filter questions in question bank | Week 7 | Done
34 | Question Bank Detail View | FE | Student | Medium | Open detailed student view of a question bank item | Week 7 | Done
35 | Knowledge Analytics Summary | FE | Student | Medium | Display analytics summary by learning area | Week 7 | Done
36 | Knowledge Analytics Topic Breakdown | FE | Student | Medium | Show topic-level breakdown and progress data | Week 7 | Done
37 | Leaderboard Ranking View | FE | Student | Simple | Display student leaderboard ranking list | Week 7 | Done
38 | Streak Badge View | FE | Student | Simple | Display streak count and badge collection | Week 7 | Done
39 | Wallet Balance Overview | FE | Student | Medium | Show current wallet and subscription information | Week 8 | Done
40 | Top-up Constraints View | FE | Student | Simple | Display wallet top-up rules and limits | Week 8 | Done
41 | Top-up Package Selection | FE | Student | Medium | Show selectable top-up packages for purchase | Week 8 | Done
42 | Top-up Payment Creation | FE | Student | Medium | Create top-up payment order from FE | Week 8 | Done
43 | Purchase History Listing | FE | Student | Simple | Display student purchase history list | Week 8 | Done
44 | Purchase Detail View | FE | Student | Simple | Open a specific payment transaction detail | Week 8 | Done
45 | Flashcard Deck View | FE | Student | Medium | Render flashcard learning interface | Week 8 | Done
46 | Flashcard Navigation | FE | Student | Simple | Move between flashcards during review flow | Week 8 | Done
47 | BYOS Upload Form | FE | Student | Complex | Render upload form for user-provided documents | Week 8 | Done
48 | BYOS File Submit Action | FE | Student | Complex | Submit BYOS file upload to backend | Week 8 | Done
49 | BYOS Document List | FE | Student | Complex | List uploaded BYOS documents in workspace | Week 8 | Done
50 | BYOS Document Delete Action | FE | Student | Medium | Delete uploaded BYOS document from workspace | Week 8 | Done
51 | BYOS Document Preview | FE | Student | Complex | Preview parsed content of a BYOS document | Week 9 | Done
52 | BYOS Document Download | FE | Student | Simple | Download original BYOS document file | Week 9 | Done
53 | Extraction Draft Display | FE | Student | Complex | Display extracted draft content from uploaded document | Week 9 | Done
54 | Extraction Draft Topic Review | FE | Student | Medium | Show extracted topics and chapter-based draft data | Week 9 | Done
55 | Generate BYOS Input Setup | FE | AI | Complex | Set parameters for question generation from BYOS source | Week 9 | Doing
56 | Generate BYOS Submit Action | FE | AI | Complex | Send BYOS generation review request to backend | Week 9 | Doing
57 | Generate BYOS Result Review | FE | AI | Complex | Display generated question review result for BYOS flow | Week 9 | Doing
58 | Generate System Input Setup | FE | AI | Complex | Set parameters for question generation from system source | Week 9 | Doing
59 | Generate System Submit Action | FE | AI | Complex | Send system generation review request to backend | Week 9 | Doing
60 | Generate System Result Review | FE | AI | Complex | Display generated question review result for system flow | Week 9 | Doing
61 | Data Approval Preview View | FE | AI | Complex | Render preview page for generated or extracted data approval | Week 9 | Doing
62 | Student Scaffold Navigation | FE | Student | Medium | Student shell, sidebar, and workspace scaffold behavior | Week 9 | Done
63 | Admin Dashboard Widgets | FE | Admin | Medium | Render admin dashboard summary widgets | Week 10 | Done
64 | Admin Dashboard Navigation | FE | Admin | Simple | Provide quick navigation from admin dashboard | Week 10 | Done
65 | Admin Users Listing | FE | Admin | Medium | Display list of managed users for admin | Week 10 | Done
66 | Admin User Detail View | FE | Admin | Medium | Open details of a selected user | Week 10 | Done
67 | Admin User Status Update | FE | Admin | Medium | Change user status from admin UI | Week 10 | Done
68 | Course List Management View | FE | Admin | Medium | Display course list and management actions | Week 10 | Done
69 | Course Create/Edit Form | FE | Admin | Medium | Create or edit course information from admin UI | Week 10 | Done
70 | Course Status Toggle | FE | Admin | Simple | Enable or disable course status from admin UI | Week 10 | Done
71 | Practice Setup Listing | FE | Admin | Complex | Display practice setup list and overview | Week 10 | Done
72 | Practice Setup Detail View | FE | Admin | Complex | Open and inspect a practice setup item | Week 10 | Done
73 | Practice Setup Create Action | FE | Admin | Complex | Create new practice configuration | Week 10 | Done
74 | Practice Setup Update Action | FE | Admin | Complex | Update existing practice configuration | Week 10 | Done
75 | Wallet Package Listing | FE | Admin | Medium | Display wallet top-up package list | Week 10 | Done
76 | Wallet Package Create/Edit | FE | Admin | Medium | Create and edit top-up package settings | Week 10 | Done
77 | Wallet Package Status Toggle | FE | Admin | Simple | Update status of wallet package | Week 10 | Done
78 | Admin Question Listing | FE | Admin | Complex | Display question management list for admin | Week 11 | Done
79 | Admin Question Detail View | FE | Admin | Complex | Inspect full detail of a question item | Week 11 | Done
80 | Admin Question Update Action | FE | Admin | Complex | Edit question metadata or content | Week 11 | Done
81 | Admin Question Import Action | FE | Admin | Complex | Import question data into system | Week 11 | Done
82 | Admin Question Publish/Disable | FE | Admin | Medium | Publish, reject, or disable question status | Week 11 | Done
83 | Admin Document Listing | FE | Admin | Complex | Display document inventory and operation list | Week 11 | Done
84 | Admin Document Preview | FE | Admin | Complex | Preview managed document content for admin | Week 11 | Done
85 | Admin Document Upload/Edit | FE | Admin | Complex | Upload or edit managed documents | Week 11 | Done
86 | Admin Document Toggle/Delete | FE | Admin | Medium | Toggle document active state or delete document | Week 11 | Done
87 | Admin Generate Questions Input | FE | Admin | Complex | Configure admin-triggered generation parameters | Week 11 | Done
88 | Admin Generate Questions Submit | FE | Admin | Complex | Trigger admin generation workflow | Week 11 | Done
89 | Admin Generate Questions Review | FE | Admin | Complex | Review generated questions before publish | Week 11 | Done
90 | Provider Credentials Listing | FE | Admin | Medium | Display saved AI provider credentials | Week 12 | Doing
91 | Provider Credential Create | FE | Admin | Complex | Add new AI provider credential | Week 12 | Doing
92 | Provider Credential Update/Delete | FE | Admin | Complex | Edit or delete AI provider credential | Week 12 | Doing
93 | Provider Models Reload View | FE | Admin | Medium | Trigger provider reload and inspect model list | Week 12 | Doing
94 | AI Agent Listing | FE | Admin | Medium | Display configured AI agents | Week 12 | Doing
95 | AI Agent Detail Update | FE | Admin | Complex | Update AI agent routing or settings | Week 12 | Doing
96 | Rule Artifact Listing | FE | Admin | Complex | Display rule artifacts and versions | Week 12 | Doing
97 | Rule Artifact Create Version | FE | Admin | Complex | Create artifact and add new version | Week 12 | Doing
98 | Rule Artifact Activate/Delete | FE | Admin | Complex | Activate or delete artifact/version records | Week 12 | Doing
99 | Billing Config View | FE | Admin | Medium | Display AI billing configuration values | Week 12 | Doing
100 | Billing Config Update | FE | Admin | Complex | Update AI billing configuration from admin page | Week 12 | Doing
101 | Billing Transactions View | FE | Admin | Medium | Display AI billing transaction list | Week 12 | Doing
102 | Billing Summary View | FE | Admin | Medium | Display billing summary metrics | Week 12 | Doing
103 | Usage Logs Listing | FE | Admin | Complex | Display AI usage logs and filters | Week 12 | Doing
104 | Usage Summary Dashboard | FE | Admin | Medium | Display AI usage summary dashboard | Week 12 | Doing
105 | Artifact Usage Summary View | FE | Admin | Medium | Display usage summary grouped by artifact | Week 12 | Doing
106 | User Usage Summary View | FE | Admin | Medium | Display usage summary grouped by user | Week 12 | Doing
107 | Runtime Health View | FE | Admin | Medium | Display AI runtime health indicators | Week 12 | Doing
108 | Mentor Feedback Logs View | FE | Admin | Medium | Display mentor feedback log records | Week 12 | Doing
109 | API Probe Request Form | FE | Admin | Complex | Manual request form for API smoke probing | Week 12 | Doing
110 | API Probe Result Display | FE | Admin | Complex | Display structured probe result and metadata | Week 12 | Doing
111 | Gatekeeper Smoke Form | FE | Admin | Complex | Input form for gatekeeper smoke testing | Week 12 | Done
112 | Gatekeeper Smoke Result | FE | Admin | Complex | Display gatekeeper smoke result and meta | Week 12 | Done
113 | Extracted Content Smoke Form | FE | Admin | Complex | Input form for extracted content smoke testing | Week 12 | Done
114 | Extracted Content Smoke Result | FE | Admin | Complex | Display extracted content smoke output | Week 12 | Done
115 | Embedding Smoke Form | FE | Admin | Complex | Input form for embedding smoke testing | Week 12 | Done
116 | Embedding Smoke Result | FE | Admin | Complex | Display embedding smoke result and chunk data | Week 12 | Done
117 | Retrieval Plan Smoke Form | FE | Admin | Complex | Input form for retrieval plan smoke testing | Week 12 | Done
118 | Retrieval Plan Smoke Result | FE | Admin | Complex | Display retrieval planning output | Week 12 | Done
119 | Question Review Smoke Form | FE | Admin | Complex | Input form for question generation review smoke test | Week 12 | Done
120 | Question Review Smoke Result | FE | Admin | Complex | Display question generation review smoke output | Week 12 | Done
121 | Code Mentor Smoke Form | FE | Admin | Complex | Input form for code mentor smoke testing | Week 12 | Done
122 | Code Mentor Smoke Result | FE | Admin | Complex | Display mentor smoke feedback and billing result | Week 12 | Done
123 | Traffic Analytics View | FE | Admin | Medium | Display admin traffic analytics information | Week 12 | Done
124 | Auth Google Endpoint | BE | Common | Medium | POST api/auth/google authenticate with Google token | Week 5 | Done
125 | Auth Refresh Endpoint | BE | Common | Medium | POST api/auth/refresh renew access session | Week 5 | Done
126 | Auth Me Endpoint | BE | Common | Simple | GET api/auth/me return authenticated user profile | Week 5 | Done
127 | Auth Logout Endpoint | BE | Common | Simple | POST api/auth/logout revoke refresh session | Week 5 | Done
128 | User Get Profile Endpoint | BE | Common | Simple | GET api/user/profile load user profile | Week 5 | Done
129 | User Update Profile Endpoint | BE | Common | Medium | PUT api/user/profile update user information | Week 5 | Done
130 | User Practice History Endpoint | BE | Common | Medium | GET api/user/practice-history return user history | Week 5 | Done
131 | Admin User List Endpoint | BE | Admin | Medium | GET admin user list for management | Week 5 | Done
132 | Admin User Detail Endpoint | BE | Admin | Simple | GET admin user detail by id | Week 5 | Done
133 | Admin User Status Patch | BE | Admin | Medium | PATCH admin user status update | Week 5 | Done
134 | Course Create Endpoint | BE | Core | Medium | POST course create new course | Week 6 | Done
135 | Course Detail Endpoint | BE | Core | Simple | GET course by id | Week 6 | Done
136 | Course List Endpoint | BE | Core | Simple | GET course list | Week 6 | Done
137 | Course Update Endpoint | BE | Core | Medium | PUT course update existing course | Week 6 | Done
138 | Course Delete Endpoint | BE | Core | Simple | DELETE course remove course | Week 6 | Done
139 | Course Status Patch | BE | Core | Simple | PATCH course status toggle | Week 6 | Done
140 | Student Course List Endpoint | BE | Student | Simple | GET student courses list | Week 6 | Done
141 | Student Course Detail Endpoint | BE | Student | Simple | GET student course detail | Week 6 | Done
142 | Exam Create Endpoint | BE | Core | Medium | POST exam create new exam | Week 6 | Done
143 | Exam Detail Endpoint | BE | Core | Simple | GET exam detail by id | Week 6 | Done
144 | Exam List Endpoint | BE | Core | Simple | GET exam list | Week 6 | Done
145 | Student Exam Detail Endpoint | BE | Student | Medium | GET student exam detail by id | Week 6 | Done
146 | Student Exam List Endpoint | BE | Student | Medium | GET student exams by course | Week 6 | Done
147 | Student Exam Library Endpoint | BE | Student | Medium | GET student exam library | Week 6 | Done
148 | Student System Exam Library Endpoint | BE | Student | Medium | GET student system exam library | Week 6 | Done
149 | Student Exam Config Documents | BE | Student | Medium | GET exam config documents by course | Week 6 | Done
150 | Student Exam Config Question Pool | BE | Student | Medium | GET question pool for exam config | Week 6 | Done
151 | Student Exam Start Endpoint | BE | Student | Medium | POST student exam config start | Week 6 | Done
152 | FE Question List Endpoint | BE | Core | Medium | GET FE question list | Week 6 | Done
153 | FE Question Detail Endpoint | BE | Core | Simple | GET FE question detail by id | Week 6 | Done
154 | FE Question Import Endpoint | BE | Core | Complex | POST FE question import | Week 6 | Done
155 | FE Question Update Endpoint | BE | Core | Complex | PUT FE question update | Week 6 | Done
156 | FE Question Status Patch | BE | Core | Medium | PATCH FE question status | Week 6 | Done
157 | Practice Start Endpoint | BE | Student | Medium | POST practice/start create practice session | Week 7 | Done
158 | Practice Session Detail | BE | Student | Medium | GET practice session detail | Week 7 | Done
159 | Practice Active Session Lookup | BE | Student | Simple | GET active session for exam | Week 7 | Done
160 | Practice End Endpoint | BE | Student | Medium | POST end practice session | Week 7 | Done
161 | Practice Draft Code Save | BE | Student | Medium | PUT draft code for session | Week 7 | Done
162 | Practice Pause Endpoint | BE | Student | Simple | POST pause practice session | Week 7 | Done
163 | Practice Resume Endpoint | BE | Student | Simple | POST resume practice session | Week 7 | Done
164 | Practice History Endpoint | BE | Student | Medium | GET practice history | Week 7 | Done
165 | Question Detail Endpoint | BE | Core | Medium | GET question detail by id | Week 7 | Done
166 | Question List Endpoint | BE | Core | Complex | GET question list with filters | Week 7 | Done
167 | Question Import Endpoint | BE | Core | Complex | POST general question import | Week 7 | Done
168 | Question Update Endpoint | BE | Core | Complex | PUT question update | Week 7 | Done
169 | Question Disable Endpoint | BE | Core | Medium | PUT disable question | Week 7 | Done
170 | Question Publish Endpoint | BE | Core | Medium | PUT publish question | Week 7 | Done
171 | Question Reject Endpoint | BE | Core | Medium | PUT reject question | Week 7 | Done
172 | Question Delete Endpoint | BE | Core | Simple | DELETE question | Week 7 | Done
173 | Admin Question List Endpoint | BE | Admin | Complex | GET admin question list | Week 7 | Done
174 | Admin Question Update Endpoint | BE | Admin | Complex | PUT admin question update | Week 7 | Done
175 | Admin Question Disable Endpoint | BE | Admin | Medium | PUT admin disable question | Week 7 | Done
176 | Admin Question Import Endpoint | BE | Admin | Complex | POST admin question import | Week 7 | Done
177 | Student Question Bank List | BE | Student | Complex | GET student question bank list | Week 7 | Done
178 | Student Question Tags Endpoint | BE | Student | Simple | GET topic tags for question bank | Week 7 | Done
179 | Student Question Detail Endpoint | BE | Student | Medium | GET student question detail | Week 7 | Done
180 | Student Question Delete Endpoint | BE | Student | Simple | DELETE student saved/generated question | Week 7 | Done
181 | Student Question Publish Endpoint | BE | Student | Medium | PUT publish student question item | Week 7 | Done
182 | Student Analytics Summary | BE | Student | Medium | GET student analytics summary | Week 8 | Done
183 | Gamification Streak Endpoint | BE | Student | Simple | GET current streak data | Week 8 | Done
184 | Gamification Badges Endpoint | BE | Student | Simple | GET earned badges | Week 8 | Done
185 | Gamification Leaderboard Endpoint | BE | Student | Simple | GET leaderboard data | Week 8 | Done
186 | Submit FE Answers Endpoint | BE | Core | Complex | POST submission/fe for FE answers | Week 8 | Done
187 | Submit PE Answers Endpoint | BE | Core | Complex | POST submission/pe for PE grading | Week 8 | Done
188 | Run PE Code Endpoint | BE | Core | Complex | POST submission/pe/run for code execution | Week 8 | Done
189 | Get PE Submission Detail | BE | Core | Medium | GET PE submission by id | Week 8 | Done
190 | Get PE Session Submissions | BE | Core | Medium | GET PE submissions by session id | Week 8 | Done
191 | Get Session Submissions | BE | Core | Medium | GET all submissions for session | Week 8 | Done
192 | Create Mentor Feedback | BE | AI | Complex | POST submission mentor feedback generation | Week 8 | Done
193 | Get Mentor Feedback Latest | BE | AI | Medium | GET latest mentor feedback for submission | Week 8 | Done
194 | Get Mentor Feedback History | BE | AI | Medium | GET mentor feedback history for submission | Week 8 | Done
195 | Wallet Constraints Endpoint | BE | Student | Simple | GET wallet top-up constraints | Week 8 | Done
196 | Wallet Package List Endpoint | BE | Student | Simple | GET top-up package list | Week 8 | Done
197 | Wallet Create Payment Endpoint | BE | Student | Medium | POST create wallet top-up payment | Week 8 | Done
198 | Wallet Payment History Endpoint | BE | Student | Medium | GET wallet payment history | Week 8 | Done
199 | Wallet Payment Detail Endpoint | BE | Student | Simple | GET wallet payment detail by id | Week 8 | Done
200 | Wallet Cancel Payment Endpoint | BE | Student | Simple | POST cancel top-up payment | Week 8 | Done
201 | Wallet AI Transactions Endpoint | BE | Student | Medium | GET AI wallet transaction history | Week 8 | Done
202 | Payment Webhook Endpoint | BE | AI/Payment | Medium | POST payment webhook callback | Week 8 | Done
203 | Admin Package List Endpoint | BE | Admin | Simple | GET admin top-up packages | Week 8 | Done
204 | Admin Package Create Endpoint | BE | Admin | Medium | POST create top-up package | Week 8 | Done
205 | Admin Package Update Endpoint | BE | Admin | Medium | PUT update top-up package | Week 8 | Done
206 | Admin Package Status Patch | BE | Admin | Simple | PATCH top-up package status | Week 8 | Done
207 | Student BYOS Upload Endpoint | BE | Student | Complex | POST student document BYOS upload | Week 9 | Done
208 | Student Document Preview Endpoint | BE | Student | Complex | GET student document preview | Week 9 | Done
209 | Student Document List Endpoint | BE | Student | Medium | GET student document list | Week 9 | Done
210 | Student Document Download Endpoint | BE | Student | Simple | GET student document download | Week 9 | Done
211 | Student Document Delete Endpoint | BE | Student | Simple | DELETE student document | Week 9 | Done
212 | Student Extraction Draft Endpoint | BE | Student | Complex | GET extraction draft for student document | Week 9 | Done
213 | Student Document Topics Endpoint | BE | Student | Medium | GET student document topics | Week 9 | Done
214 | Student Document Chapters Endpoint | BE | Student | Medium | GET student document chapters | Week 9 | Done
215 | Student Chapter Topics Endpoint | BE | Student | Medium | GET topics by chapter for student document | Week 9 | Done
216 | Student Document Chapter-Topics | BE | Student | Medium | GET chapter-topics aggregation for student document | Week 9 | Done
217 | Admin Document Upload Endpoint | BE | Admin | Complex | POST admin document upload | Week 9 | Done
218 | Admin Document List Endpoint | BE | Admin | Medium | GET admin document list | Week 9 | Done
219 | Admin Document Preview Endpoint | BE | Admin | Complex | GET admin document preview | Week 9 | Done
220 | Admin Document Download Endpoint | BE | Admin | Simple | GET admin document download | Week 9 | Done
221 | Admin Document Edit Endpoint | BE | Admin | Complex | PUT admin document edit | Week 9 | Done
222 | Admin Document Toggle Active | BE | Admin | Simple | PUT admin document active toggle | Week 9 | Done
223 | Admin Document Draft Endpoint | BE | Admin | Complex | GET admin document extraction draft | Week 9 | Done
224 | Admin Document Delete Endpoint | BE | Admin | Simple | DELETE admin document | Week 9 | Done
225 | AI Generate Review Endpoint | BE | AI | Complex | POST generate-review general AI question generation | Week 10 | Done
226 | AI Generate Review System | BE | AI | Complex | POST generate-review/system | Week 10 | Done
227 | AI Generate Review BYOS | BE | AI | Complex | POST generate-review/byos | Week 10 | Done
228 | Publish Generated Question | BE | AI | Medium | PUT publish generated question | Week 10 | Done
229 | Delete Generated Question | BE | AI | Simple | DELETE generated question | Week 10 | Done
230 | AI Retrieval Plan Endpoint | BE | AI | Complex | POST retrieval plan generation | Week 10 | Done
231 | Retrieval Course Topics Endpoint | BE | AI | Medium | GET topics by course for retrieval setup | Week 10 | Done
232 | Retrieval Course Documents | BE | AI | Medium | GET documents by course for retrieval setup | Week 10 | Done
233 | Retrieval Document Chapters | BE | AI | Medium | GET chapters by document for retrieval setup | Week 10 | Done
234 | Retrieval Chapter Topics | BE | AI | Medium | GET topics by chapter in retrieval flow | Week 10 | Done
235 | Retrieval Chapter-Topics Aggregate | BE | AI | Medium | GET chapter-topics retrieval aggregation | Week 10 | Doing
236 | Retrieval Context Pack Detail | BE | AI | Medium | GET context pack detail by id | Week 10 | Doing
237 | Retrieval Context Pack List | BE | AI | Medium | GET context pack list | Week 10 | Doing
238 | Retrieval Context Pack Stale Update | BE | AI | Medium | PUT mark context pack stale | Week 10 | Doing
239 | Admin Billing Config Get | BE | Admin | Medium | GET AI billing config | Week 11 | Doing
240 | Admin Billing Config Update | BE | Admin | Complex | PUT AI billing config | Week 11 | Doing
241 | Admin Billing Transactions List | BE | Admin | Medium | GET AI billing transactions | Week 11 | Doing
242 | Admin Billing Summary Get | BE | Admin | Medium | GET AI billing summary | Week 11 | Doing
243 | Admin Billing Refund Action | BE | Admin | Complex | POST refund AI billing transaction | Week 11 | Cancelled
244 | Admin Usage Logs Get | BE | Admin | Complex | GET AI usage logs | Week 11 | Doing
245 | Admin Usage Summary Get | BE | Admin | Medium | GET AI usage summary | Week 11 | Doing
246 | Admin Artifact Usage Summary | BE | Admin | Medium | GET usage summary by artifacts | Week 11 | Doing
247 | Admin User Usage Summary | BE | Admin | Medium | GET usage summary by users | Week 11 | Doing
248 | Admin Runtime Health Get | BE | Admin | Medium | GET runtime health | Week 11 | Doing
249 | Admin Mentor Feedback List | BE | Admin | Medium | GET mentor feedback logs | Week 11 | Doing
250 | Admin Provider Credentials Get | BE | Admin | Medium | GET provider credentials list | Week 11 | Done
251 | Admin Provider Credential Create | BE | Admin | Complex | POST provider credential | Week 11 | Done
252 | Admin Provider Credential Update | BE | Admin | Complex | PUT provider credential | Week 11 | Done
253 | Admin Provider Credential Delete | BE | Admin | Simple | DELETE provider credential by provider | Week 11 | Done
254 | Admin Provider Credential Replace | BE | Admin | Complex | PUT provider-specific credential update | Week 11 | Done
255 | Admin Provider Credential Batch | BE | Admin | Complex | PUT batch provider credentials | Week 11 | Done
256 | Admin Provider Reload | BE | Admin | Medium | POST provider reload | Week 11 | Done
257 | Admin Provider Models Get | BE | Admin | Medium | GET provider models by provider name | Week 11 | Done
258 | Admin Agents List | BE | Admin | Medium | GET AI agents list | Week 11 | Doing
259 | Admin Agent Detail | BE | Admin | Medium | GET AI agent detail by role | Week 11 | Doing
260 | Admin Agent Update | BE | Admin | Complex | PUT AI agent config by role | Week 11 | Doing
261 | Admin Smoke Gatekeeper | BE | Admin | Complex | POST smoke gatekeeper execution | Week 12 | Done
262 | Admin Smoke Extracted Content | BE | Admin | Complex | POST smoke extracted content execution | Week 12 | Done
263 | Admin Smoke Embedding | BE | Admin | Complex | POST smoke embedding execution | Week 12 | Done
264 | Admin Smoke Retrieval Plan | BE | Admin | Complex | POST smoke retrieval plan execution | Week 12 | Done
265 | Admin Smoke Question Review | BE | Admin | Complex | POST smoke question generation review | Week 12 | Done
266 | Admin Smoke Code Mentor | BE | Admin | Complex | POST smoke code mentor execution | Week 12 | Doing
267 | Rule Artifact List Endpoint | BE | Admin | Complex | GET rule artifacts list | Week 12 | Doing
268 | Rule Artifact Create Endpoint | BE | Admin | Complex | POST create rule artifact | Week 12 | Doing
269 | Rule Artifact Add Version | BE | Admin | Complex | POST add artifact version | Week 12 | Doing
270 | Rule Artifact Activate Version | BE | Admin | Medium | POST activate artifact version | Week 12 | Doing
271 | Rule Artifact Delete Version | BE | Admin | Medium | DELETE artifact version | Week 12 | Doing
272 | Rule Artifact Delete Artifact | BE | Admin | Medium | DELETE artifact | Week 12 | Doing
273 | AI Execution Service | BE | AI | Complex | Coordinate AI request execution across providers | Week 12 | Doing
274 | AI Prompt Service | BE | AI | Complex | Resolve and manage AI prompt payload/version data | Week 12 | Doing
275 | AI Gatekeeper Service | BE | AI | Complex | Gatekeeper validation for content eligibility | Week 12 | Doing
276 | AI Extracted Content Service | BE | AI | Complex | Normalize and process extracted document content | Week 12 | Doing
277 | AI Embedding Tagging Service | BE | AI | Complex | Embedding and auto-tagging pipeline | Week 12 | Doing
278 | Code Mentor Service | BE | AI | Complex | Generate mentor feedback from submission data | Week 12 | Doing
279 | Question Review Service | BE | AI | Complex | Review generated questions before persistence | Week 12 | Doing
280 | Retrieval Planner Service | BE | AI | Complex | Build retrieval context packs for AI generation | Week 12 | Doing
281 | AI Billing Service | BE | AI/Payment | Complex | Calculate and record AI VND billing usage | Week 12 | Done
282 | Submission Grading Processor | BE | Core | Complex | Process grading pipeline for submissions | Week 12 | Doing
283 | Submission Result Evaluator | BE | Core | Complex | Evaluate submission results and final verdicts | Week 12 | Doing
284 | Judge0 Worker Job | BE | Core | Complex | Background worker for Judge0 execution polling | Week 12 | Doing
285 | Document Processing Worker Job | BE | Core | Complex | Background worker for document extraction jobs | Week 12 | Done
286 | Payment Status Worker Job | BE | AI/Payment | Medium | Background worker for payment status refresh | Week 13 | Done
(*) You can rate the functions' complexity based on the number of fields on the screens or the number of transactions in the function, with the details as below
| simple |  | <=7 fields | <=3 transactions
| medium |  | <=15 fields | <= 7 transactions
| complex |  | >15 fields | > 7 transactions
In which:
fields: screen components or database table fields
transactions: action buttons, user or database transactions

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
1 | Login page text still used Sign in instead of Login | Inconsistent wording on the authentication screen | Low | Hung | 2026-07-24 | 2026-08-01 | Closed | Confirmed in code: login CTA text uses Login.
2 | Payment history column order needs adjustment | Users may have difficulty scanning payment records quickly | Medium | Hung | 2026-07-25 | 2026-08-03 | Closed | Confirmed in code: Payment History columns are OrderCode, Provider, Amount, Status, Date, Action.
3 | Admin use cases 71-73 are not fully implemented | Admin workflow remains incomplete for required use cases | High | Minh | 2026-07-29 |  | Open | Need to add missing admin functions for UC 71-73
4 | UC-13 is missing functionality | Required use case cannot be demonstrated during review | Medium | Sang | 2026-07-29 |  | Open
5 | UC-63 is missing functionality | Required use case cannot be demonstrated during review | Medium | Sang | 2026-07-29 | 2026-08-05 | Closed
6 | UC-24 is missing functionality | Required use case cannot be demonstrated during review | Medium | Sang | 2026-07-29 | 2026-08-05 | Closed
7 | UC-111 is missing functionality | Required use case cannot be demonstrated during review | Medium | Sang | 2026-07-29 |  | Open
8 | UC-128 to UC-139 implemented but not confirmed | Delivered scope may still contain hidden gaps before acceptance | Medium | Sang | 2026-07-30 |  | Open | Implemented, pending confirmation
9 | UC-143 is missing functionality | Required use case cannot be demonstrated during review | High | Sang | 2026-07-30 |  | Open | Feature not available yet
10 | UC-119 needs further research for AI testing | AI test scope may be incomplete or unclear | Medium | Sang | 2026-07-31 |  | Open | Research item for AI test section
11 | Student question bank needs to be added and admin role needs update | Student learning flow and admin permissions are incomplete | High | Sang | 2026-07-28 | 2026-08-04 | Closed | Student question bank exists in code, but admin role update still needs confirmation.
12 | Exam config screen needs to be revised toward practice setup | Current screen structure may not match intended workflow | Medium | Hung | 2026-07-31 | 2026-08-06 | Closed | Possible rename or redesign to practice setup
13 | Admin upload document screen is missing | Admin cannot manage document upload workflow | High | Hung | 2026-07-27 | 2026-08-04 | Closed | Confirmed in code: AdminDocumentManagementPage contains admin upload document UI.
14 | Skeleton code saving needs to be fixed | Code templates may be lost or stored incorrectly | High | Sang | 2026-07-31 | 2026-08-06 | Closed | Review save flow for skeleton code
15 | Generated question UI needs redesign | Generated content review experience is hard to use | Medium | Hung | 2026-07-31 | 2026-08-06 | Closed | Redesign question generation result section
16 | AI Code Mentor saving logic needs review | Mentor data may not persist correctly | High | Sang | 2026-07-31 | 2026-08-06 | Closed | Recheck AI Code Mentor persistence
17 | MCQ screen needs countdown timer | Users lack clear time tracking during MCQ test | Medium | Hung | 2026-07-29 | 2026-08-05 | Closed | Confirmed in code: MCQ page shows elapsed timer.
18 | MCQ screen needs redo action | Users cannot restart MCQ flow when needed | Medium | Hung | 2026-08-01 | 2026-08-06 | Closed | Add redo button for MCQ
19 | UC-89 functionality needs to be added | Required use case is missing from the system | High | Sang | 2026-08-01 | 2026-08-06 | Closed | Implement UC-89
20 | UC-90 needs reintegration into library | Library workflow may be incomplete or inconsistent | Medium | Sang | 2026-08-01 | 2026-08-06 | Closed | Reintegrate UC-90 with library flow
21 | Draft code auto-save needs to be completed | Users may lose in-progress coding work | High | Sang | 2026-07-28 | 2026-08-06 | Closed | Confirmed in code: draft code is persisted and autosaved in StudentLaunchPage.
22 | Upload document pricing needs review | Incorrect billing may affect user trust and payment accuracy | High | Sang | 2026-08-01 | 2026-08-07 | Closed | Review cost calculation for document upload
23 | Practice history needs filter by type | Users cannot filter history effectively | Medium | Hung | 2026-07-30 | 2026-08-05 | Closed | Confirmed in code: Practice History has Exam Type filter.
24 | PE flow needs redo action | Users cannot quickly retake PE practice from result flow | Medium | Hung | 2026-08-02 | 2026-08-06 | Closed | Add redo button for PE
25 | Question list and question detail screen need to be added | Question browsing flow is incomplete | High | Hung | 2026-07-29 | 2026-08-05 | Closed | Confirmed in code: StudentQuestionBankPage includes list and detail view.
26 | Judge0 grading for multi-question exams needs review | Scoring may be wrong when exam contains multiple coding questions | High | Sang | 2026-08-02 | 2026-08-06 | Closed | Verify Judge0 grading for multi-question exams
27 | Remove Ready status from student document list | Student document UI contains unnecessary state display | Low | Hung | 2026-07-30 | 2026-08-04 | Closed | Confirmed in code: student document list no longer renders Ready label in the list UI.
28 | PE testcase scoring must be zero if any testcase fails | Current scoring rule may not match business requirement | High | Sang | 2026-08-02 | 2026-08-06 | Closed | If one testcase fails then score must be 0

## Defects
PROJECT DEFECTS
Feature | Function/Screen | Tester | Defect Description | Assign To | Status | Notes
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending

## Q&A
PROJECT Q&A
Date | Question | By | Priority | Status | Note (answer, other notes)
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open